## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Shivam Mahesh Awasare
Document Created On: | 2023-01-08
Version: | 5.3
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Progra 2023 - <DOMAIN NAME> Project Schedule
|  | PROJECT START DATE | 2023-01-08
|  | Display Week Sr No | 1 | [10 empty] | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | time axis 2023-01-02 to 2023-03-05
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2023-01-02 to 2023-03-05
1 | [Project Initialization]
1.1 | Week 1 | Project Initialization | Project Kickoff | Define project scope |  | Me | 2023-08-01 | 2023-08-01 |  | 2 | Completed | 1
|  |  |  | Prepare project plan |  | Me | 2023-08-03 | 2023-08-03 |  | 4 | Completed
|  |  |  | Review and finalize plan |  | Me | 2023-08-04 | 2023-08-04 |  | 2 | Completed
2 | [Development Phase]
2.1 | Week 2 | Development Phase | Backend Setup | Install Flask | Flask | Me | 2023-08-07 | 2023-08-07 |  | 3 | Completed
|  |  |  | Design database schema |  | Me | 2023-08-08 | 2023-08-09 |  | 6 | Completed
|  |  |  | Frontend UI Design | HTML/CSS | Me | 2023-08-08 | 2023-08-10 |  | 8 | Completed
|  |  |  | Frontend Implementation | Browser | Me | 2023-08-10 | 2023-08-12 |  | 10 | Completed
|  |  |  | Backend Development | VS Code | Me | 2023-08-10 | 2023-08-14 |  | 15 | Completed
|  |  |  | Testing and Debugging |  | Me | 2023-08-13 | 2023-08-17 |  | 12 | Completed
3 | [Testing and Refinement]
3.1 | Week 3 | Testing and Refnement | User Acceptance Testing | Test basic functionality | Backend Setup | Me | 2023-08-18 | 2023-08-19 |  | 8 | Completed
|  |  |  | Test user interactions | Browser | Me | 2023-08-20 | 2023-08-21 |  | 8 | Completed
|  |  |  | Debug and fix issues |  | Me | 2023-08-22 | 2023-08-24 |  | 10 | Completed
4 | [Final Touch]
4.1 | Week 4 | Final Touch | Adding more Data | Adding Basic Queries |  | Me | 2023-08-25 | 2023-08-29 |  | 10 | Completed
|  |  |  | Adding more FAQ |  | Me | 2023-08-25 | 2023-08-26 |  | 2 | Completed
|  |  | Styling the Front end | CSS Restructure |  | Me | 2023-08-27 | 2023-08-28 |  | 5 | Completed
|  |  |  | Final Testing |  | Me | 2023-08-29 | 2023-08-31 |  | 3 | Completed
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you